## Slide 1
Project Scheduling with Precedence Constraints
A Graph-Based Dual-Engine Optimization System for Data Structures and Algorithms
Directed Acyclic Graphs • Overwatch (Managerial CPM) • Overdrive (Gamified Quests)

## Slide 2
The Dual-Engine Concept
Overwatch Mode
Sturdy managerial view focused on reliability: Critical Path Method, deadlock detection, and precise float/slack computation for schedule assurance.
Overdrive Mode
High-octane gamified layer that converts bottlenecks into tiered quests, streaks, and EXP rewards to boost developer engagement and prioritization.

## Slide 3
Theoretical Graph Modeling
Model: DAG G = (V, E). Each vertex v ∈ V represents a task with a duration; each directed edge (u → v) is a precedence constraint requiring u before v.
Storage: Adjacency list for O(V + E) space.
Operations: Edge traversal and neighborhood queries in O(V + E) time.
Assumptions: No cycles; tasks have non-negative durations.

## Slide 4
Pipeline Architecture
01
1. Task ingestion
Parse task metadata, durations, and dependency edges.
02
2. Kahn's cycle detection & topological sort
Detect cycles; produce an execution order if acyclic.
03
3. CPM calculation
Compute EST/EFT and LST/LFT; identify critical path(s).
04
4. Dual rendering
Render Overwatch dashboard and Overdrive quest map simultaneously.

## Slide 5
Overwatch Mode — Manager Dashboard
Operational view designed for correctness and predictability.
Deadlock-free ordering
Topological ordering ensures feasible execution sequences when DAG validated.
Critical Path Identification
Tasks with zero slack are flagged as bottlenecks for prioritization and contingency planning.
EST / EFT / LST / LFT
Earliest and latest time boundaries computed per task enable precise float calculations.

## Slide 6
Algorithmic Complexity & Benchmarks
The core algorithms operate in linear time relative to graph size:
Topological sort & Kahn's cycle detection: O(V + E) time, O(V + E) space.
CPM (forward/backward passes): O(V + E) — single pass per direction.
Memory: adjacency lists keep footprint minimal for large task graphs (thousands+ nodes).
Designed for real-time resolution: typical production graphs (10k–100k edges) complete within interactive latency targets.

## Slide 7
Overdrive Mode — Gamified Quest Engine
Translate scheduling signals into behavioral incentives to guide team focus without sacrificing correctness.
Boss Quests
Critical-path tasks become boss-level challenges with team-wide priorities.
Rarity & Rewards
Task rarity (Common→Legendary) maps to XP multipliers and visibility boosts.
Streaks & Priority Queues
Priority-queue–based scheduling rewards consecutive on-time completions with increasing EXP.

## Slide 8
Task Rarity Matrix
Rarity | Definition / Examples
Common | Basic setup tasks: small, independent, low-degree vertices.
Uncommon | Standard tasks with a few dependencies; short-duration contributors.
Rare | Hub nodes with high in/out degree — potential local bottlenecks.
Epic | Sub-critical milestones whose delay affects downstream parallelism.
Legendary | Apex critical-path boss tasks: zero slack, highest priority in Overwatch and Overdrive.

## Slide 9
Ingestion
Validation
Optimization
Dual Rendering
Lifecycle overview: ingest tasks → validate acyclicity and constraints → optimize schedule via CPM and priority heuristics → render both managerial and gamified views for execution.

## Slide 10
Expected Outcomes & Next Steps
Correct, conflict-free schedules
Topological guarantees plus CPM ensure valid execution orders and transparent slack metrics.
Precise bottleneck detection
Zero-slack tasks surfaced for mitigation and targeted resource allocation.
Engagement through gamification
Overdrive mechanics encourage timely completions and strategic parallelism without compromising correctness.
Deliverables
Prototype implementation, benchmark suite (O(V+E) verification), demo dashboards for Overwatch & Overdrive, and integration guide.
Questions?
Combine algorithmic rigor with behavioral design — ready for technical review and live demo.